## Instructions
Management Process Step | Column | Description
Identify | ID | Enter a unique risk identifier.
| Title | Enter a short title of the risk.
| Description (If… then) | Enter a long form description of the risk. A risk event statement states (1) what might happen in the future (IF) and (2) the possible impact on the project (THEN). "Weather" is not a risk event statement. "Bad weather may delay the project schedule" is a risk event statement.
| Risk Realized? | Select Yes or No to indicate whether or not the risk has become an issue.
| Status | Select the appropriate status from the status field based on risk management lifecycle phase.
| Risk Owner | Enter the name of the person tasked with owning the risk.
| IPR? | Select Yes or No to indicate whether or not the risk should be reviewed during the IPR. This should also align with the IPR template risk areas.
| Risk Source | Select a risk source (i.e., the driver that causes risks in a project).
Analyze | Risk Category | Select a risk category (e.g., the areas for which all risk categories were considered when identifying and analyzing risks). Review each Risk Category to consider potential risks in all categories.
| Impact Area | Select an area of impact.
| Trend | Select the appropriate trending direction based on the ongoing outcomes of the mitigation strategies as well as the execution of associated action plans. Is the risk improving, in severity level based on mitigations.
| Probability | Select a numerical assessment from 1 to 5 of the probability of occurence (almost certain (5) to rare (1)).
| Impact | Select a numerical assessment from 1 to 5 of the potential consequence (extreme (5) to negligible (1)).
| Severity | Value is auto populated. A numerical assessment of probability multiplied by impact (manageable (green), threatening (yellow), or serious (red)).
Plan Response | Response Strategy | Select a strategy to address the risk/issue.
| Response Plan | Enter the specific action items and due dates required to reduce the impact of the risk/issue event on the project.
| Trigger Event | Enter an event that describes an indicator that might turn a risk into an issue (realized risk/issue).
| Contingency Plan | Used as an alternative for action if expected results from response plan fail to materialize. A contingency plan is sometimes referred to as "Plan B."
Monitor and Control | Status | Select Identified, Analysis Complete, Planning Complete, Triggered, Resolved, Retired, or Issue. If the risk event materializes, then the status changes to Issue.
| Trend | Select Improving, Steady, Deteriorating, or Retired as the risk is being monitored.
| Notes and Comments | Enter a short description of the progress made. (Longer detail can be entered into a corrective action log, action item log, or other project specific tracking mechanism. If using the risk log to track status and updates, preface each entry into this field with your first and last name initials and the date the update is made followed by the updated comments - e.g., BL 20150801: This is the update for today.)
| Close Rationale | Enter the reason and date for closing a risk/issue.

## Risk Threshold Guidelines
Risk Threshold Guidelines | [7 empty] | Risk Severity Matrix
Probability |  |  | Impact |  |  |  |  | Probability | Impact
Level | Probability of Event |  | Level | Risk/Issue Impact | Cost or Schedule Impact | Scope or Quality Examples | Reliability Examples | 5 | 5 | 10 | 15 | 20 | 25
5 | Almost Certain | >80% – risk/issue event expected to occur | 5 | Extreme | >20% | End product fails to meet customer needs (legislation requirements) resulting in congressional inquiries or punitive damages | Defects cause unpredictable problems in all software | 4 | 4 | 8 | 12 | 16 | 20
4 | Likely | 60-80% – risk/issue event more likely to occur | 4 | Major | 10-20% | Reduction in functionality or usability unacceptable to customer | Major defects after third month in implementation | 3 | 3 | 6 | 9 | 12 | 15
3 | Moderate | 40-59% – risk/issue event has a moderate chance of occurring | 3 | Moderate | 5-10% | Major impact in functionality or usability requiring customer approval | Defects that interrupt business operations sporadically and not for any length of time | 2 | 2 | 4 | 6 | 8 | 10
2 | Unlikely | 20-39% – risk/issue event less likely to occur | 2 | Minor | <5% | Relatively minor impact in functionality or usability | Defects that do not interrupt business operations | 1 | 1 | 2 | 3 | 4 | 5
1 | Rare | <20% – risk/issue event not expected to occur | 1 | Negligible | No or negligible variance | Very minor impact in functionality or usability | Minor defects—such as spelling or help—but no implications to IT or business operations; can wait until another release to address |  | 1 | 2 | 3 | 4 | 5

## Risk Log
ID | Title | Description (If… then..) | Risk Realized? | Status | Risk Owner | IPR? | Risk Source | Risk Category | Impact Area | Trend | Probability | Impact | Severity | Trigger Event | Response Plan | Response Strategy | Contingency Plan | Notes and Comments | Close Rationale
1 | Weather Forecast | Bad weather may delay the project. | No | Identified | Beth Leonard | Yes | Scope | Strategic or External | Schedule | Improving | 2 | 3 | 6 | TE: Severe weather watch issued by National Weather Service. | RP: 1. Notify the team of forecaset. 2. Implement emergency procedures SOP. | Monitor |  | BL 20160501: Insert notes here (detailed) AA 20160401: Insert update here (detailed). No change made. Or reduced probability, trend of risk is improving. | Added to Issue Log; see Issue #5
2 | [6 empty] | Schedule | [5 empty] | 0
3 | [12 empty] | 0
4 | [12 empty] | 0
5 | [12 empty] | 0
6 | [12 empty] | 0
7 | [12 empty] | 0
8 | [12 empty] | 0
9 | [12 empty] | 0
10 | [12 empty] | 0

## Issue Log
# | Issue Description | Severity | Corrective Action | Realized Risk ID # | Realized Impact # | Status | Opened Date | Closed Date | Issue Owner | Comments
1
Note on E1: If issue was originally identified as a risk, enter risk # from Risk Log, otherwise "N/A"
Note on F1: If issue is a realized risk, enter risk impact from Risk Log

## Decision Log
ID #: | Topic Area/Meeting: | Priority | Decision/ Outcome Description | Date Decision /Outcome Identified: | Date of Decision | Status | Decision Makers / Stakeholders: | Supporting Documentation and Information: | Action Owner: | Comments / Status Updates: | Date of Change or Decision Reversal: | Rationale for Changed Decision:
1 | Identify the main topic area of the change, decision, action, or outcome |  | Documented detailed notes to describe the outcomes of the meeting, decisions made, or follow on actions to be implemented. | mm/dd/yyyy | mm/dd/yyyy |  | Identify the primary decision makers responsible and/or part of the decision making process. E.g., Customer Bob was primary decision maker, and the following team members were included in the meeting/discussion: Mary, Joe, Terrance, Rahul. | Include specific detailed information related to the decisions made, items raised that need action, outcomes of discussions/meetings, and other pertinent information. | Insert first and last name. | Include additional status updates related to the decisions or outcomes. Be specific and provide detailed information for item raised, decisions made, and other pertinent information. Format for updates: First Name Initial Last Name Initial YYYY/mm/DD: Status Update (e.g., BL 20160501: Implemented step one of the corrective action, based on change in scope requested by the customer on 04/01/2015. Scope change included reduction of sprint release to include removal of user stories 1, 2, 3, and 4, which were moved to the backlog. | mm/dd/yyyy | Specific detailed information as to why a change to the initial decision occurred. Identify who made what decision, what the actual decision or outcome was, and on what date. Include any other involved stakeholders.

## Ref Definitions
Category | Description | Examples
Strategic or External | This allows you to look at external risks, which may affect your organization such as changes in the external market space environment in which you operate. It also lets you look at setting organizational objectives and ensuring you set the right ones and then meet them. | Risks stemming from customer relationship management activities, business partnerships, contracts, industry/market changes, acquisitions, intellectual property rights, business portfolio, strategic planning and development, new business/growth opportunities, target setting vision and goals, investor relations, human capital, reputation, etc.
Operational | This looks at the risks, which arise from the products and services you deliver or the activities you carry out on a program or within a department, as well as risks associated with the employment of staff. | Risk/issue stemming from information technology, scope/requirements, personnel, deployment of skilled team members, technical knowledge, training, effective utilization of project equipment inventories, deficient hardware, antiquated technology, business disruption, innovation, requirements, complexity and interfaces, performance and reliability, supply chain, product/service quality, product/service liability, product/service fit for use and purpose, decision making, project estimating, planning, controlling, communication, etc.
Compliance | This category looks at the legislative framework within which your organization operates, ensuring compliance with applicable laws, best practices, and security controls. | Risk/issue stemming from legal, regulatory, political, market practices (ITIL, ISO, CMMI, Sarbanes Oxley, etc.), general business principle (e.g., ethics), internal controls (organizational policies, processes, procedures), data privacy, product security, industrial security, IT security, personnel security, etc.
Financial | This covers financial risks facing the organization in terms of internal systems, planning, funding etc. | Risk/issue stemming from the funding that impacts the effective utilization of human capital or project resources, treasury, tax, pensions, accounting and reporting, vulnerability to external business threats and market risks, fraud, revenue management, etc.

## _Names
CLIN | ImpactArea
PM | Cost
Operations | Schedule
Testing | Technical
Development | Quality
Status
Identified
Analysis Complete
Category | Planning Complete
Strategic or External | Triggered
Operational | Resolved
Compliance | Retired
Financial
Trend
Improving
Steady
Deteriorating
PI
5
4 | Type
3 | Risk
2 | Issue
1
ResponseStrategy
Avoid | RiskSource | AltRiskSource
Transfer | Scope | Ambiguous Requirements
Control | Schedule | Unrealistic Schedule
Accept | Resources | Complex Design
Monitor | Quality | New Technology
| Risks/Issue Management | Unavailable Resources/Skills
| Budget | Inadequate Communications
| Deliverables | Other
Ambiguous requirements | Stakeholders
Unrealistic schedule | Value to Client
Complex design | Subcontractors
New technology | Back Office Support
Unavailable resources/skills | Customer Satisfaction
Inadequate communication
Other